## Resource plan
Weeks of vacation / year | 4.5
Vacation rate | 8.333%
|  | Total |  |  | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 |  | Comments
Headcount (theoritical) |  | 71.5 |  |  | 6 | 6 | 6.5 | 10 | 10 | 9 | 8 | 8 | 8 |  | = Hiring forecast, state your assumptions
Butts In Seat (actual) |  | 59.5 |  |  | 6 | 6 | 6.5 | 8 | 8 | 7 | 6 | 6 | 6 | 0 | = Actual committed count, the people you know will be there by that time.
Scheduled |  | 58.9583 |  |  | 6 | 6 | 6.5417 | 7.8333 | 7.8333 | 7 | 5.9167 | 5.9167 | 5.9167 |  | = Scheduled work
ΔHC |  | 12.5417 |  | (-) is overcommited | 0 | 0 | -0.041667 | 2.1667 | 2.1667 | 2 | 2.0833 | 2.0833 | 2.0833 |  | = Scheduled work - theoritical headcount
ΔBIS |  | 0.54167 |  |  | 0 | 0 | -0.041667 | 0.16667 | 0.16667 | 0 | 0.083333 | 0.083333 | 0.083333 |  | = Scheduled work - actual headcount
Features | P | Scheduled | FTE/Quarter | Who | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 |  | Comments
Non features
Oncall |  | 8.5 |  |  | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | State assumptions, e.g. "Assuming production ramping up in May"
Vacations |  | 5.9583 |  |  | 0.5 | 0.5 | 0.54167 | 0.83333 | 0.83333 | 0.75 | 0.66667 | 0.66667 | 0.66667 |  | Counting a standardized rate of vacation, configure. When planning this should be enough
Hackathon |  | 1.75 |  |  | 2022-09-01: 1.75 |  | 1 week in september
Product A |  | 8 | 2.6667 | Alice, Bob | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 0.5 |  |  |  |  | Scope is A, B, maybe C
Project B |  | 16.5 | 5.5 | Bern, Max, Eric, Jed | 2 | 1.5 | 2 | 2 | 2 | 1 | 2 | 2 | 2 |  | Assuming we want continuous investment through the year
Feature C |  | 7.5 | 2.5 | Nabilla, Jed | 2022-04-01: 1.5; 2022-05-01: 1.5; 2022-06-01: 1.5; 2022-07-01: 1.5; 2022-08-01: 1.5 |  | Assuming PoC, Pilot, then continued investments
Initiative D |  | 2.25 | 0.75 | Alice | 2022-10-01: 0.75; 2022-11-01: 0.75; 2022-12-01: 0.75
Prototype E |  | 5.5 | 1.8333 | Nabilla, Jed | 2022-09-01: 1; 2022-10-01: 1.5; 2022-11-01: 1.5; 2022-12-01: 1.5 |  | Assuming dependencies done by August. Will increase count if hiring works
Feature F (won't do) |  | 0 | 0
Refactoring ABC |  | 0 | 0
Intern project |  | 3 | 1 | bar: 2022-07-01 to 2022-09-01
|  | 0 | 0
|  | 0 | 0
--- |  | 0 | 0
Team | BIS | Levels | Specialty | Assignment | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01
Alice | x | L5 | FS | Product A | bar: 2022-04-01 to 2022-12-01
Bob | x | L6 | BE | Product A | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 |  | Taking a LOA in Sept
Bern | x | L5 | BE | Project B | bar: 2022-04-01 to 2022-12-01
Max | x | L4 | FS | Project B | bar: 2022-04-01 to 2022-12-01
Nabilla | x | L4 | FS | Feature C, Prototype E | bar: 2022-04-01 to 2022-12-01
Jed | x | L7 | FS | Project B, then Feature C | bar: 2022-04-01 to 2022-12-01
Eric | x | L5 | FS | Feature B |  |  | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 |  | Joining mid-may, assuming onboarding takes 4 weeks
Headcount 1 |  | L5 | FS | Prototype E | [10 empty] | Hoping to recruit in June | bar: 2022-07-01 to 2022-12-01
Headcount 2 |  | L5 | BE | Prototype E | [10 empty] | Hoping to recruit in June | bar: 2022-07-01 to 2022-12-01
Intern | x | L3 | NA | Intern project | bar: 2022-07-01 to 2022-09-01
---
|  | BE | 3
|  | FS | 6
|  | FE | 0